## workload statistics
initiation | 5
requirments | 10
System analysis and design | 17
development | 31
testing | 28
training | 1
maintenance | 5

## Estimated workload
No. | stage | task | Days | total days
1 | initiation | Bids | 5 | 5
2 | requirments | analysis | 6 | 10
|  | prototpye design | 4
3 | System analysis and design | methodology | 5 | 17
|  | function design | 4
|  | Interface design | 3
|  | flow-process analysis | 4
|  | database design | 1
4 | development | build development environment | 6 | 31
|  | goods display. | 2
|  | user login and regist and password recover | 4
|  | goods auction | 3
|  | generate order | 3
|  | order display | 3
|  | make appointments | 3
|  | User management (admin) | 2
|  | Order management(admin) | 2
|  | goods management（admin） | 2
|  | About us and contact us | 1
5 | testing | integration testing | 14 | 28
|  | System testing | 7
|  | acceptance testing | 7
6 | go to live\training\maintenance | prepare to go live | 2 | 8
|  | Client training | 1
|  | maintenance | 5
TOTAL |  |  |  | 94